## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Making Team strong in Project Fundamentals & Prerequisites
|  | 1 | Poject Understanding
|  | 2 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data
|  | 3 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline
|  | 4 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 |  | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 45949 | 45950 | 45951 | 45952 | 45953 | 45954 | 45955 | 45956 | 45957 | 45958 | 45959 |  | 45961 | 45962 | 45963
SPRINT 1 BACKLOG
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Charan
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th sep | Emmadi Srikar | Leant and practiced the python concepts | Completed |  | installation | python intro | keywords | Data types | Diff Datatypes |  |  | Flowcontrol | Function Part-1 | Function part-2 | Modules |  | OOPS | Packages | control packages
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Hatim Mandviwala | Python Fundamentals | Completed |  | installation | Introduction | Keywords | Data types | Types of datatype |  |  | Flowcontrol | Functions/Methods |  | Modules |  | OOPS | Packages | Flow Control
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Pragathi Y | I learnt and practiced fundamentals of python like loops,functions ,running code etc | Ongoing |  | installation | Introduction | Keywords | Data types | Types of datatype |  |  | Flowcontrol | Functions/Methods |  | Modules
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Aditi Gupta | Revised and practiced python | Completed |  | installation | introduction | keywords | Data types | Types of datatype |  |  | Flowcontrol | functionsp1 | functionsp2 | module |  | OOPS | package | control package
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Koduri Vikitha | practice and Learning the python fundmentals | Completed |  | python instalation | introduction | Python Keyword | intoduction to Data types | practice on datatypes |  |  | Flow controls in python | Functions part-1 | Functions part-2 | Modules Introduction |  | OOPS | package | control package
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Guda Karthik Kumar Reddy | Revised all the basic python concepts and practiced focussing on topics like loops, functions, oops | Completed |  | installation | introduction | keywords | Data types | Types of datatype |  |  | Flowcontrol | Functions part-1 | Functions part-2 | Modules |  | OOPS | Packages | Flow Control
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Sreeja Manthena | Revised the python fundamentals | Ongoing |  | installation | introduction | keywords | Data types | Diff DataTypes |  |  | Flowcontrol | Functions part-1 | Functions part-2 | Modules |  | OOPS | Packages | Flow Control
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th sep | Sri Varshini | Revised all the basic python concepts and practiced focussing on topics like functions, oops | completed |  | installation | introduction | Keywords | Data types | Types of Data types |  |  | Flow controls in python | Function part 1 | Functions Part 2 | Modules |  | OOPS | packages | Flow control
1 | 1 | learning important and basic fundamentals that are required for the project | 5th Sep | 19th | kranthi swamika varma | learnt the basic and important fundamentals of python | Ongoing |  | python& jupiter installation | introduction of python | keywords | data types | Types of Data types |  |  | Flowcontrol | Function part 1 | Functions Part 2 | python Modules |  | OOPS
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th sep | S Jahnavi | I learnt and practiced fundamentals of python like loops,functions ,running code etc | Ongoing |  | installation | Introduction | Keywords | Data types | Types of Data types |  |  | Flow control | Function Part 1 | Function part 2 | python modules |  | OOPS | packages | control packages
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th sep | Chetti Jayaveer | Learnt the basics and concepts of Python | Ongoing |  | Installion of python | Introduction | Keywords | Datatypes | Types of Datatypes |  |  | Flow control | Function Part 1 | Functions Part 2 | Python Modules |  | OOPS
1 | 1 | Learning Fundamentals for project | 5th Sep | 19th sep | Basutkar Sony | Python fundamentals | Completed |  | Python Installation | Introduction | Keywords | Datatypes | Naming Conventions | Variables | Data types practice | Flow Control | Functions part-1 | Functions part-2 | Modules |  | OOPS | Packages | Flow Control practice
1 | 1 | Learning Fundamentals for project | 5th Sep | 19th Sep | Chintha Naga Prasanna | Recap All the Fundamentals that required for Project Understanding | Completed |  | Python Installation | Introduction to Python | Keywords | Datatypes | Naming Conventions |  |  | Flow Control | Functions part-1 | Functions Part 2 | Modules |  | OOPS | Packages | Control Practice
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th Sep | Meghana Nilesh Patil | Learnt and practiced the python programming langaunge fundamentals and OOP concepts | Completed |  | Python & jupyter installation | Introduction to Python | Keywords | Datatypes | Naming Conventions |  |  | Flow Control | Functions part-1 | Functions Part 2 | Modules |  | OOPS | Packages | Control Practice
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd oct | Aditi Gupta | Learnt the concepts of NLP and project understoodlearnt and practiced preprocessing , cleaning and preparing training | Done |  | NLP Introduction, Milestone 1 | practice on nlp | Project understand | Interactive session/api | (created service account and retreiving data from sheets |  | Pandas DataFrame | Practice and revised dataframes |  | Data Preprocessing | tokenisation, lemmesiationand stop words removal |  | EDA | Feature Engineering | Prepared data input for training LLM
2 | 2 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Koduri Vikitha | Understand of project discussion and Fundmentals of NLP and what is the steps in the project , Gained hands on experience with basic NLP through python programming | Done |  | NLP Introduction ,Milestone 1 |  | Project understand | Interactive session/api | Concepts on Tokenisation & lemmazation |  | Dataframe(Pandas) | Removal of stop words | EDA | Feature Engineering |  |  | About EDA and prepared training input LLM
2 | 2 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Chintha Naga Prasanna | Learn how to Preprocess the Data for Training | Done |  | NLP Introduction |  | Project understand | Interactive session/api | Concepts on Tokenisation & lemmazation |  | Dataframe | Removal of stop words |  | Loading Data From Google Sheets and Pre-process the Data | Pin to Pin Explanation of Python Codes |  | EDA | Feature Engineering | Preparing data input for training LLM
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Emmadi Srikar | learnt about NLP,pre-processing historical data and prepared the training input for LLM | Done |  | NLP introduction | project understanding | Created service account and loading data from sheets | Service account and API | loading the dataset and milestone 1 introduction | discussed about dataframe,text preprocessing |  | Tokenization |  | lemmatization,stopword removal and code step by step explanation |  | About EDA |  | Feature Engineering | prepared training input for LLM
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Guda Karthik Kumar Reddy | Learnt the basics of NLP concepts and applied them using python code, Learnt and practiced pre-processing the loaded historical data like cleaning the noisy data, lemmatization, tokenization, EDA, and training LLM | Done |  | Introduction to NLP |  | Project Understanding | Service account and API | Milestone 1 introduction | Loading the historical data from sheets | DataFrames | Tokenization |  |  | EDA | Feature Engineering |  | Finally training the LLM based on the data
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Meghana Nilesh Patil | learnt about pre-processing historical ticket data , text processsing ,EDA ,preparing training | Done |  | Introduction to NLP | Project Understang | Create Service account and load data from sheets | service account and API | Load the data from sheets | Milestone 1 Intro. | DataFrames | Tokenization | lemmatization,stopword removal |  | EDA | Feature Engineering | Prepared data input for training LLM
2 | 1 | Establish infrastructure for ticket data integration and pre processing of historical ticket data | 20th sep | 3rd Oct | Hatim Mandviwala | Learnt Basic NLP concepts and how to Preprocess and Clean Data | Done | Day 1 45949: Intoduction To NLP; Day 2 45950: Project Understanding and Delivering; Day 3 45951: Create Service Account And Load Data from Sheets using it using Python; Day 5 45953: DataFrames; Day 6 45954: Introduction to Milestone 1; Day 7 45955: Loading historical Data and Intro to Data Preprocessing; Day 10 45958: Tokenization,lemmatization | EDA and Stop Words Removal,Feature Engineering |  | Preparing Final Data for Training LLM
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | A. Nikhil Sai Ram Reddy | Learnt and understood the basic concepts of NLP and applied them using python | Done | Day 1 45949: Introduction to NLP; Day 3 45951: Understanding the problem statement; Day 5 45953: Milestone 1; Day 6 45954: Milestone 1; Day 7 45955: Dataframe(Pandas); Day 10 45958: Pre-processing data
2 | 2 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Basutkar Sony | NLP basics, Preprocessing data | Completed |  | Intoduction To NLP | Project Understanding | Interaction session | Milestone-1 | Creating service account | Collecting data from Google Sheets |  | About pandas dataframes,methods,attributes |  | Preprocessing the historical tickets data | Tokenisation,lemmazation | Stopword removing | EDA | Feature Engineering | Prepare Training Input for LLM
3 | 1 | Knowledge Categorization &Tagging Engine
2 | 1 | Establish infrastructure for ticket data integration | 20th sep | 3rd oct | Pragathi Y | Studied methods to preprocess and clean training data for model preparation Gained hands on experience with basic NLP through python programming | Done |  | Intro to Milestone 1,Brief abt NLP | Importing historical datasets and learning the basics of data preprocessing |  | Create Service Account And Load Data from Sheets using it using Python | Tokenization | Lemmatisation | EDA | Stop word elimination for NLP preprocessing |  | Feature Engineering | Preparing the cleaned and processed data for large language model training |  |  |  | Preparing Final Data for Training LLM
2 | 1 | Establish infrastructure for ticket data integration and pre processing of historical ticket data | 20th sep | 3rd Oct | Sreeja Manthena | Learnt the basic nlp concepts and practised them | Done |  | Intro to nlp | practised on nlp and revised the concepts | intro of the project and its present limitaions, how this project overcomes them | Interactive Session and learnt new things from our friends and discussed how to explain the project to the interviwer in an effective way. | Creating service account | Loads the data from the google sheet | DataFrames intro | practised and revised dataframes | disscussed dataframe methods and attributes | Data pre processing | Tokenization and stop word removal | Lemmatisation | EDA | Feature Engineering | Prepared the input data for training the llm
2 | 1 | Establishling the infrastructure for ticket data integration and Pre-process Historical Ticket Data | 20th sep | 3rd oct | Sri Varshini | Gained hands on experience as it is a real world project and Studied methods to preprocess and clean training data for model preparation | Done |  | introduction to NLP, Intro to Milestone 1 | understanding the project requirements and Importing historical datasets and learning the basics of data preprocessing | Understanding the problem statement clearly | Loading the dataset and creating the service account | Tokenisation | Lemmatization | EDA | removing the stop words | Data frames | Feature Engineering |  |  | Preparing the cleaned data and pre processing it for the LLM training
2 | 2 |  |  |  | Turn on screen reader support
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd oct | kranthi swamika varma | Learnt the concepts of NLP and project understoodlearnt and practiced preprocessing , cleaning and preparing training | done |  | Intoduction To NLP | project understanding | Breif introduction to project needs and provide the steps and the solutions | Create Service Account And Load Data from Sheets using it using Python | Concepts on Tokenisation & lemmazation |  | EDA | practised and revised dataframes | disscussed dataframe methods and attributes | disscussed dataframe methods and attributes | disscussed dataframe methods and attributes | disscussed dataframe methods and attributes | EDA | Feature Engineering | Prepared the input data for training the llm
2 | 1 | Establish infrastructure for ticket data integration and pre processing of historical ticket data | 20th sep | 3rd oct | S Jahnavi | learnt about pre-processing historical ticket data , text processsing ,EDA ,preparing training | done |  | Intoduction To NLP | Project Understanding | Created service account and loading data from sheets | Service account and API | tokenization , Milestone 1 | Lemmatization | EDA | practised and revised dataframes | disscussed dataframe methods and attributes | Feature Engineering | Tokenization and stop word removal | Stopword removing | Preparing the cleaned data and pre processing it for the LLM training | Feature Engineering | Prepared the input data for training the llm
2 | 1 | Establish infrastructure for ticket data integration & pre processing of historical ticket data | 20th Sep | 3rd oct | Chetti Jayaveer | Learnt how to preprocess historical ticket data cleaning preparing for training data using nlp | Done |  | introduction to nlp | project understanding | created service account and loading data from sheets | Service account and API | tokenizartion | lemmatization | EDA | Dataframes | Dataframe methods and attributes | Feature Engineering | Stop word removing | lematization | Preparing the cleaned data and pre processing it for the LLM training | Feature Engineering | Prepared the input data for training the llm
3 | 1 | Knowledge Categorization &Tagging Engine | 4th oct | 18th Oct | Sri Varshini | Tags And Categorization | Ongoing | Day 1 45949: Tagging and Categorisation
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th Oct | 18th Oct | Chintha Naga Prasanna | Knowledge Categorization & Tagging Engine Prompt Engineering & Automation Pipeline | Ongoing |  | Practice(4th Oct) | Practice(5th Oct) | Knowledge Categorization and Tagging Engine(6th Oct) | Designing the Prompt for LLM and Creating GROQ API Keys(7th Oct) | Definitions of Prompt, Prompt engineering ,Why prompt Engineering and Different types of Prompting( 8th Oct) | Explanation about few Shot Prompting and Classification pipline with LLaMa 3.3(9th Oct) | Discussing Regarding Validation, Accuracy and Confusion Matrix(10th Oct) | Orientation Session Regarding the Complete Project Upadates (11th Oct) | Assignment 1 & 2(12th Oct) | Practice on Classification code with different data(13th Oct) | Explanation about complete Archietecture Workflow(14th Oct) | Code Explanation for Building a Semantic Search system by using FAISS(15th Oct)
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th OCT | 18th OCT | Pragathi Y | Knowledge Categorization and Tagging Engine, and understanding Prompt Engineering with Automation Pipelines | Ongoing |  | (3rd oct) Introduction to Milestone 2 | (4th oct) revised and wrapped previous tasks | (5th oct ) Practice | (6th oct) Categorisation and tagging | Designing the prompt with llm and created groq api key | Prompt engineering and automation pipeline | Validation,Accuracy & Confusion Matrix | Orientation Session Regarding the Complete Project Upadates (11th Oct) | Assignment 1 & 2(12th Oct) | Practice on Classification code with different data and categorisation | Explanation about Archietecture Workflow | FAISS | Workflow for Building a Semantic Search System using FAISS | Building the Real-Time API
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th OCT | 18th OCT | Koduri Vikitha | Introduction to Prompt Engineering,and automation pipileine ,understand of Knowledge Categorization | Ongoing | Day 1 45949: Milestone 2; Day 2 45950: Learning,practice; Day 3 45951: Knowledge Categorization and Tagging Engine; Day 4 45952: creating the groq api key hands on experience and prompting llm ,use and importance of prompt engineering,applications; Day 6 45954: Prompt engineering and automation pipeline
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th OCT | 18th OCT | Meghana Nilesh Patil | Knowledge Categorization &Tagging Engine,Prompt Engineering & Automation Pipeline | Ongoing |  | Introduction of Milestone2 | Revised the previous topics | Knowledge Categorization and Tagging Engine | Designing prompt for LLM & Creating GROQ API key | Prompt Engineering | Automation Pipeline and Few Shot Prompting | Validation,Accuracy & Confusion Matrix | Interaction about project updates | Assignment 1 | Classification code with different data | Discuss on Archietecture Flow | Create semantic search by using FAISS
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th OCT | 18th OCT | A. Nikhil Sai Ram Reddy | Knowledge Categorization & Tagging Engine Prompt Engineering & Automation Pipeline | Ongoing | Day 1 45949: Milestone 2; Day 2 45950: Practiced previous class; Day 3 45951: Knowledge Categorization and Tagging Engine; Day 4 45952: Designing the Prompt for LLM and Creating GROQ API Keys; Day 5 45953: Prompt Engineering; Day 6 45954: Prompt Engineering and Automation Pipeline
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th Oct | 18th oct | Aditi Gupta | Knowledge Categorization & Tagging Engine Prompt Engineering & Automation Pipeline | Done |  | Introduction of milestone 2 | Revised the previous topics | knowledge categorisation and tagging engine | prompting llm and creating Groq api keys | prompt engineering | few shot prompt engineering and automation pipeline | Validation, accuracy and confusion matrix | project updates discussion | Assignment 1 completion | Classification code with diff data | Architecture flow | FIASS semantic search | Semantic search system workflow | Building realtime API
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th Oct | 18th Oct | Guda Karthik Kumar Reddy | Learning and understanding about knowledge categorization and tagging engine, Learnt how to give efficient prompts using the concepts of Promt engineering, building automation pipelines | Ongoing | Day 1 45949: Introduction of milestone 2; Day 2 45950: Revision and practice on previous concepts; Day 3 45951: Knowledge Categorization and Tagging Engine; Day 4 45952: Giving and designing prompts for LLM and creation of GROQ API Key; Day 5 45953: Prompt Engineering; Day 6 45954: Giving prompt using Few Shot Prompt Engineering technique and Automation Pipeline
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th Oct | 18th oct | Basutkar Sony | Knowledge Categorization &Tagging Engine,Prompt Engineering & Automation Pipeline | Completed |  | Revised NLP concepts | Learned about ollama & how llms are used in our project | Knowledge Categorization and Tagging Engine | Designing prompt for LLM & Creating GROQ API key | Prompt Engineering | Few shot prompting and Automation pipeline | Classification Pipeline with LLaMA 3.3 (Groq API) | Interaction about project updates | Worked on Assignment 1 | Validation and Accuracy Evaluation | Steps for Evaluating model | Introduction to system Architecture | Workflow for Building a Semantic Search System using FAISS | Building the Real-Time API | Worked on Assignment-2
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th Oct | 18th Oct | Hatim Mandviwala | Knowledge Categorization &Tagging Engine,Prompt Engineering & Automation Pipeline | Ongoing |  | Inroduction to Milestone 2 | Revision and Practise of previous Topics | Knowledge Categorization and Tagging Engine | Designing prompt for LLM & Creating GROQ API key | Prompt engineering | Automation Pipeline and Few shot Prompt | Confusion Matrix,Accuracy of Model,Validation | Discussion on project updates | Assignment 1 Completed
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th Oct | 18th Oct | Sreeja Manthena | Understanding knowledge categorization and tagging systems, along with prompt engineering and automation pipelines. | Ongoing |  | Introduction of milestone 2 | Revised and practised the previous topics and worked on the project | Knowledge Categorization and Tagging Engine | Gained hands-on experience in creating and using Groq API keys while working with LLM prompting. Explored the significance of prompt engineering | Prompt Engineering | Prompt engineering and automation pipeline | Validation,Accuracy and Confusion Matrix related Concepts | Project Updates related discussion | Assignment 1 and 2 completed | Classification code with diff data | Disscussion on archietecture Workflow | How to create an Semantic search system using FIASS | Workflow for building Semantic Search | Building a Real-time API
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th oct | 18th oct | Emmadi Srikar | learnt about tickets,category,tags,examples and prompt engineering and also practiced LLaMA3 model example hands on ,automation pipeline | ongoing | Day 1 45949: Introduction of milestone 2; Day 2 45950: revised the previous topics covered; Day 3 45951: Knowledge Categorization and Tagging Engine; Day 4 45952: Desingining the prompt for LLM and done process for creating API key; Day 5 45953: prompt engineering; Day 6 45954: Automation pipeline and few shot prompt
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th OCT | 18th OCT | kranthi swamika varma | learnt about Knowledge Categorization & Tagging Engine Prompt Engineering & Automation Pipeline | ongoing | Day 1 45949: Introduction of milestone 2; Day 2 45950: Revision and practice on previous concepts; Day 3 45951: Knowledge Categorization and Tagging Engine; Day 4 45952: Designing prompt for LLM & Creating GROQ API key; Day 5 45953: prompt engineering; Day 6 45954: Automation Pipeline and Few shot Prompt
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th OCT | 18th OCT | Chetti Jayaveer | Knowledge Categorization &Tagging Engine,Prompt Engineering & Automation Pipeline | ongoing | Day 1 45949: introduction of milestone 2; Day 2 45950: Revision and practice on previous concepts; Day 3 45951: Knowledge Categorization and Tagging Engine; Day 4 45952: Designing prompt for LLM & Creating GROQ API key; Day 5 45953: prompt engineering; Day 6 45954: Automation Pipeline and Few shot Prompt
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th oct | 18th oct | S Jahnavi | Learning and understanding about knowledge categorization and tagging engine, Learnt how to give efficient prompts using the concepts of Promt engineering, building automation pipelines | ongoing |  | introduction of milestone 2 | Revision and Practise of previous Topics | Knowledge Categorization and Tagging Engine | Giving and designing prompts for LLM and creation of GROQ API Key | prompt engineering | Automation Pipeline and Few shot Prompt | Confusion Matrix,Accuracy of Model,Validation | project updates discussion | Worked on Assignment 1 | Classification code with diff data | Explanation about Archietecture Workflow | Create semantic search by using FAISS | Workflow for Building a Semantic Search System using FAISS | Building the Real-Time API
4
[9 empty] | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Basutkar Sony | Realtime recommendation Introduction & System Architecture | Ongoing |  | Revised about Fast API | Revised about Embeddings | Real time API | Content Gap Analysis | Monitoring, Alerts & Automation | Streamlit Introduction | Revised Content gap analysis | Practised streamlit | Streamlit | Revised previous concepts | Building Streamlit Dashboard | Slack Integration | Project workflow | Project Integration
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th oct | 2nd Nov | Emmadi Srikar |  | Ongoing
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Pragathi Y | Realtime recommendation Introduction & System Architecture | Ongoing |  | Practice | Worked on previous session | Learnt abt Real time API | Content Gap Analysis | Monitoring, Alerts & Automation | stramlit framework and Dashboard creation | Gone through previous content | Searched abt Stramlit | Learnt abt streamlit | Revised concepts | Dashboard creation using streamlit | Slack Integration | Overview of Project workflow
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Sreeja Manthena | Realtime recommendation Introduction & System Architecture | Ongoing |  | Practice | Practice | Realtime API | Content gap analysis | Monitoring Alerts and automation | Streamlit framework and Dashboard creation | revised the concepts and worked on project | practised streamlit | learned streamlit | revised the concepts | build streamlit dashboard | Slack Integration | Overview of Project workflow | Project integration
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Meghana Nilesh Patil | Realtime recommendation Introduction & System Architecture | Ongoing |  | Practice | Practice | Realtime API | Content Gap Analysis | Monitoring, Alerts & Automation | Streamlit framework and Dashboard creation | Revised the content gap analysis | Practicing on Streamlit | Practicing on Streamlit | Revised the previous topics | Building Streamlit Dashboard | Slack Integration | Overview of Project Workflow | Project Integration
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Kranthi Swamika Varma | Realtime recommendation Introduction & System Architecture | Ongoing |  | Practice | Practice | Realtime API | Content Gap Analayisi | Monitoring, Alerts & Automation | stramlit framework and Dashboard creation | revised the concepts and worked on project | Practised streamlit | learned streamlit | Revised concepts | Dashboard creation using streamlit | Slack Integration | Overview of Project workflow | Project Integration
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Aditi Gupta | Realtime recommendation Introduction & System Architecture | Ongoing |  | Practice | Practice | Realtime API | Content Gap Analayisi | Monitoring, Alerts & Automation | Streamlit framework and Dashboard creation | revised the previous topics | Practiced Streamlit | Streamlit | Revised previous topics | Dashboard creation using streamlit | Stack Integration | Project Workflow | project integration
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th oct | 2nd Nov | S Jahnavi | Realtime recommendation Introduction & System Architecture | Ongoing |  | Practice | Practice | Realtime API | Content Gap Analaysis | Monitoring, Alerts & Automation | Streamlit framework and Dashboard creation | revised the concepts and worked on project | Practised streamlit | learned streamlit | Revised concepts | Dashboard creation using streamlit | Slack Integration | Overview of Project workflow | Project Integration
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th Oct | 2nd Nov | Koduri Vikitha | Realtime recommendation Introduction & System Architecture | Ongoing |  | 2025-10-19: Practice; 2025-10-20: Practice; 2025-10-21: Realtime API

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
4 | 4 | API Key Error

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7